## Sheet1
Task | Start date | duration | end date
Teach jetson to identify single seed | 2018-01-08 | 7 | 2018-01-15
Expand jetson to identify more seeds | 2018-01-15 | 21 | 2018-02-05
Fromulate good output from jetson | 2018-02-05 | 7 | 2018-02-12
Setup database for output | 2018-02-12 | 14 | 2018-02-26
create app that can send an image to jetson | 2018-02-26 | 7 | 2018-03-05
create user friendly app | 2018-03-05 | 14 | 2018-03-19
email output to user | 2018-03-19 | 7 | 2018-03-26